Volunteer Schedule

Prep Week through Ride Day  ·  June 23–27, 2026  ·  Lake County Fairgrounds, Lakeview, OR

TUESDAY  ·  June 23

| Time | Event / Need | Volunteer(s) |
| --- | --- | --- |
| 9:00 AM | Signage: pick up signage at Shed Quarters (wooden, plastic ones) Attach to boards, make paper signs, directional signs Placement of Gravel Route signage | Donna, Lesa, Marie |
| 10:00 AM | Confirm Safeway order pick-up for Thursday (AM or PM??) | Marie |

WEDNESDAY  ·  June 24

Waivers needed for Wednesday volunteers.

| Time | Event / Need | Volunteer(s) |
| --- | --- | --- |
| 12:00 PM | Tent set-up — check to Dayton Alves $500 Stage placement, arrange electrical for band(s) | Dayton Alves, Fairgrounds helper Marty C., Donna, Marie, David |

THURSDAY  ·  June 25

Waivers needed for new volunteers.

| Time | Event / Need | Volunteer(s) |
| --- | --- | --- |
| 8:00 – 10:00 AM | Spray paint on gravel route | Donna |
| 12:00 PM | Mt Mazama water delivered | Mt Mazama, Marie |
| 12:00 PM | Porta-potties delivered and confirm sites | Lesa |
| 12:00 PM | Tables and chairs set up; place tablecloths on each table, tape down each side Tables (2–3) for Pizza — label Tables (2) for Registration — signage labeled | Saul, David, Donna, Hugh, Marie (fairgrounds help), Marie David |
| 2:00 PM | Clean bathrooms and showers | Sara Bowersox |
| 2:00 PM? | Band set up | Marty C. |
| 3:00 PM | RV trailers to RV park (Tucker's and Griffith's) | Tim, Anneke |
| 4:00 PM | Shed Quarters (alleyway of 839 South G St) Load trailer & unload at fairgrounds | Hugh, Lesa, SAR helper, David, Saul, Tim, Marie, Donna |
| 5:00 PM | Organize headquarters items: registration area, signage Kitchen — get organized for Aide Station help | David, Donna, Lesa Marie |

FRIDAY  ·  June 26  —  Prep & Rider Check-In

Waivers for any new volunteers.

| Time | Event / Need | Volunteer(s) |
| --- | --- | --- |
| 7:00 AM | Contact police *677 — advise of cyclists on road | Marie |
| 7:00 AM | Pick up eggs, potatoes | Marie |
| 8:00 AM | Aide Station prep — wash and dry produce Sort fruit in portions and assemble cooler (as much as possible) Assemble utensils and place in collapsible boxes Label with inventory of cooler; label road or gravel ride Assemble SAG coolers — Gatorade, water Pop-up tents labeled if need be Signage up on reader board Signage on Headquarters Feather flags placed Start Line placed, generator Arrange Packet Pick-Up Event board Map board Cash box & quarters | Danné, Shar, Kit Marie Lesa Brianna David David David, Tim David, Callie? Lesa, Donna Lesa Marie |
| 1:00 PM | Cyclists check in, packet pick-up; possible late registrations Routes confirmed, wristbands secured, raffle tickets, drink tickets | Jeanne, Alan (Donna, Lesa, Marie rotating) David |
| 3:00 PM | Shake-Out Ride | Donna, Chris |
| 4:00 PM | Mobile Bar (4–9 PM) | Jennifer Simpson |
| 5:00 – 5:15 PM | Pizza volunteers — instructions on serving, gloves | Claire, Ann, Susan |
| 5:30 PM | Meet & Greet Pizza Party (5:30 – 7:00 PM) | Downtown Bakery, Committee |
| 7:00 PM | Announcements — welcome; check back in (we are in the "outback") Raffle Announce next year date — June 26th | Donna, Marie, David Cyclist — Wanda David |

SATURDAY  ·  June 27  —  RIDE DAY

| Time | Event / Need | Volunteer(s) |
| --- | --- | --- |
| 5:00 AM | Make all coffee, locate cups, cut bananas, eggs, fill urns | Lesa, Marie |
| 5:30 AM | Complete Aide Station coolers — food from fridge distributed to coolers | Marie, Shar |
| 6:00 AM | SAR — check out radios, coolers, ice, tents, water, beverage containers | Lesa |
| 6:15 AM | SAR refresher — go over food display on tables at Aide Station Wristbands for volunteer meal; ask volunteers to take photos of riders at their Aide Station Road Route signage check | Lesa, SAR |
| 6:15 AM | Registration (LATE) set-up | Jeanne, Alan, Callie |
| 6:15 AM | Pastries & Photos — display food, eggs, coffee cups, coffee | Rotary, Callie |
| 6:30 AM | Route ??? — rotating helpers | Donna, Lesa, Marie |
| 6:30 AM | SAG Meeting — signage on sweep Don stays at Willow Bridge until all cyclists are over Hwy 395 | Lesa, Tim, Don |
| 6:30 AM | "Road Helpers" — guide / stop traffic for cyclists: Center St. & Hwy 395 Hollow Bridge Rd. & Hwy 395 | Mark Smith Don Brown* |
| 6:45 AM | Announcements — welcome; check-in due to "outback"; course closes at 3 PM | Donna, Marie |
| 6:50 AM | Photographers leave | Donna, David, Chris |
| 7:00 AM | Ride Start — Craig Price (police vehicle) leads cyclists across the road; cowbell ringers | Committee |
| 7:30 AM | SAG drivers leave | Tim, Don |
| 8:00 AM | Marie leaves Headquarters and drives to 1st road Aide Station | Marie |
| 8:00 AM | Band set up — Dan Decker and Missing Identity | Callie |
| 9:00 AM | Check trash | Callie |
| 10:00 AM | Road Route TOWN signage down | Marie |
| 11:00 AM | Showers — $35 in quarters to each shower in a dish with signage | Callie |
| 11:00 AM | Lunch begins (11 – 3 PM from food truck; after that boxed in cooler) | Lee Salvidor |
| 11:00 AM | Clean kitchen, utensils, sinks, fridge, etc. | Marie, Callie |
| 12:00 PM | Live Music — Missing Identity until 4 PM | Dan Decker |
| 12:00 PM | Trash check, lunch help, greeting cyclists, check showers for change | Callie |
| 12:00 PM | School Showers open | Lesa |
| 12:00 PM | Massage Therapist starts |  |
| 1:00 – 2:00 PM | Committee back to Headquarters, meet cyclists | Committee |
| 3:00 PM | Route closes — signs packed up, Aide Stations close, final sweep | SAR, SAG |
| 3:00 PM | Lunch boxed up in coolers | Lee Salvidor |
| 4:00 – 5:00 PM | Load trailer with as much as possible without disturbing party | Committee |

VOLUNTEER DIRECTORY

Contact info as of 2026-06-14. Update this section as needed.

| First Name | Last Name | Role | Phone | Email |
| --- | --- | --- | --- | --- |
| Seth | Ballaine |  | 971-400-0330 | seth.ballaine@gmail.com |
| Don | Brown | SAG Driver | 541-840-3983 | donnwb@gmail.com |
| Sharylinn | McClain | AID Stations Food | 541-219-0892 |  |
| Kit | Thornton | AID Stations Food | 541-417-0859 |  |
| Callie | Elliot |  | 541-521-2696 |  |
| Mark | Smith |  | 505-710-4380 |  |
| Hugh | Cahill |  |  |  |
| Danné | Barry |  | 541-219-2219 |  |
| Betsy | Miller |  |  |  |
| Tim | Tucker |  | 541-417-0871 |  |
| Marty | Chaloupka |  | 971-506-6072 |  |
| Chris | Stanton |  |  |  |
| Susan | Albertson |  | 541-417-0978 |  |
| Claire | Reaume |  | 541-219-2334 |  |
| Ann | Sabin |  | 541-219-0135 |  |

Schedule and assignments are working drafts — confirm with day-of leads before relying on a specific time or person.